## Project Status
BillVyapp — Project Status Overview
The Starr Kuts Salon Management Platform ¦ Status as of 17 July 2026
Overall Project Status |  | Overall Completion
In Progress |  | 71%
Phase | Overall Status | Completion % | Reason (if Pending / Blocked)
Phase 1 — Foundation & Setup (Design System, DB Schema, Authentication) | Near Complete | 95% | Registration, email verification, and password reset are fully coded but SMTP is not configured (backend/.env — all SMTP_* values commented out), so a real self-signup user can never receive a verification email. A pre-verified demo account (demo@starrkuts.com) is used as the working login path in the meantime.
Phase 2 — MVP Core Modules (Appointments, Billing/POS, Customer CRM, Service Catalog) | In Progress | 88% | Core flows are backend-wired and passing automated E2E tests (checkout, GST, discounts, split payment, card, pending bills). Pending: WhatsApp/SMS booking and payment notifications are disabled (no provider credentials configured); no public/unauthenticated customer self-booking page exists yet; card payment is a manual reference field (no real payment gateway integrated); the UPI ID used for QR payments has not been verified as a live registered VPA.
Phase 3 — Growth Modules (Inventory, Loyalty & Membership Plans) | In Progress | 85% | Inventory and Plans/Membership are backend-wired and covered by passing E2E tests (categories, vendors, purchase orders, stock adjustments, membership CRUD, wallet transactions). Live database state could not be independently re-confirmed in this session (DB host unreachable from this environment) — recommend a fresh smoke test before external sign-off.
Phase 4 — Enterprise & Multi-Branch | Not Started | 5% | No 'Branch' data model exists in the database schema yet. A Branches page exists in the frontend but is not wired into the app's routes (orphaned code). No cross-branch access logic has been built. This is a future-release phase, not required for V1.
Phase 5 — QA & Testing | In Progress | 70% | Automated E2E suite (Playwright) passing 30/31 cases (96.8%), but Chromium-only — Firefox/WebKit sign-off still pending. Tests are not yet gated in CI on every pull request. No backend unit/API contract test suite exists. Load, performance, and security penetration testing have not been executed.
Phase 6 — DevOps & Infrastructure | In Progress | 85% | Docker Compose (dev + prod), Nginx, and GitHub Actions CI/CD to EC2 are built and present in the repo. Pending: Grafana is wired to a data source but the dashboards folder is unpopulated; production SMTP, HTTPS, and secrets have not been validated end-to-end in a live deployment.
V1 scope note: Employees, Reports/Analytics, Marketing, CEO Dashboard, AI Insights, and Settings/Administration were removed from the app entirely per client request and are not tracked above as pending work.
Basis: backend/src/routes/index.ts (25 mounted API modules), Frontend folder/src/api (24 wired API client files), backend/prisma/migrations (12 applied migrations), backend/.env, and docs/QA-E2E-Test-Report-CEO.md (Playwright run, 11 Jul 2026, 30/31 passed). Percentages are estimates based on this evidence, not a formal audit.