## Phase Status
BillVyapp — Phase / Activity Status
Source: docs/BillVyapp-Project-Status-Report-2026-08-07.md §3 · Report date: 7 August 2026 · Client: The Starr Kuts · Live: https://billvyapp.com
# | Phase / Activity | Status | Completion % | Remarks / Details
1 | UI/UX Design & Frontend Development | COMPLETE | 100% | All V1 screens, workflows, and responsive UI completed.
2 | Backend API Development | COMPLETE | 100% | Core APIs for appointments, billing, customers, inventory, memberships, messaging, and notifications completed.
3 | Database Design & Implementation | COMPLETE | 100% | Schema finalized with Prisma & MySQL (including expense delete-approval migrations).
4 | Authentication & User Management | NEAR COMPLETE | 95% | Login, RBAC, and WhatsApp OTP completed. SMTP pending for email verification and password reset.
5 | Customer Management Module | COMPLETE | 100% | Customer CRUD, filters, history, visits, memberships, wallet, and coupon WhatsApp send completed.
6 | Appointment Management | COMPLETE | 100% | Walk-in, booking, calendar, appointment lifecycle, and scheduling completed.
7 | Billing & POS Module | NEAR COMPLETE | 95% | Billing, GST, discounts, split payments, invoices, memberships, and wallets completed. Razorpay pending; UPI QR + manual confirmation in use.
8 | Inventory Management | COMPLETE | 100% | Categories, vendors, products, purchase orders, stock adjustments, and usage logs completed.
9 | Membership & Packages | COMPLETE | 100% | Membership plans, packages, wallet, and service benefits implemented.
10 | Notifications Module | NEAR COMPLETE | 90% | In-app notifications + WhatsApp (Sparklebot via BullMQ/Memurai) completed. SMS and Email pending provider credentials.
11 | Dashboard & Analytics | COMPLETE | 100% | Revenue, appointments, customers, inventory, and business KPIs implemented (rbac + admin-dashboard).
12 | Playwright Automation Testing | IN PROGRESS | 97% | Major business workflows automated and validated. Browser compatibility validation remaining.
13 | Production Deployment (Cloudflare) | COMPLETE | 100% | Deployed and live at https://billvyapp.com (Windows EC2 + Cloudflare).
14 | Production Verification | IN PROGRESS | 92% | Core production verification in progress. WhatsApp path validating; final sign-off after SMTP, SMS, Razorpay.
15 | SMTP Integration | WAITING | 0% | SMTP credentials required for email verification, password reset, invoices, and email notifications.
16 | SMS API Integration | WAITING | 0% | Waiting for SMS provider credentials. WhatsApp is the active OTP channel.
17 | WhatsApp Business API Integration | NEAR COMPLETE | 95% | Sparklebot integrated: login OTP, payment received, coupons, feedback request, appointment confirm. Templates approved. Final prod smoke pending.
18 | Payment Gateway Integration (Razorpay) | WAITING | 0% | Waiting for Razorpay merchant account and API keys. App uses UPI QR with manual payment confirmation.
19 | Production Smoke Testing | IN PROGRESS | 85% | Core modules validated. Final smoke after SMTP, SMS, and Razorpay.
20 | Production Go-Live | IN PROGRESS | 92% | Application is publicly accessible. Final sign-off depends on SMTP, SMS, and Payment Gateway.

## Summary
BillVyapp — Project Status Report
Field | Detail
Client | The Starr Kuts
Application | BillVyapp
Production URL | https://billvyapp.com
Report date | 7 August 2026
Git baseline | rbac (fa4e7bf)
Production HEAD | production/main (cb77277)